Minutes of Meeting

Thursday June 6th 2019

Meeting opened at 19:30 following D Day Beacon ceremony on the Promeande

1	Attendees –  T Larsen, R Larsen, G Holmes, D Edwards, P Read, K Watson

Apologies  –    R Harries

2	Action Point Update

Agenda Item	Owner	Descriptor

20180311a	TL	Plaque display –ongoing - Agreed that niches on Pier towers be used

AP	TL to get confirmation boards can be mounted on Pier towers

20180808i	DE	Sand Le Mere sponsor - ongoing – RH has a meeting with a Director Arranged

20181005b	RL	Enquire regarding insurance - ongoing

20181208a	DE	Source main funding - ongoing

20190109b	RH	Enquire about being on Lara King radio show – discharged, no response

20190502a	TL	Contacts at Siemens/British Steel - Siemens ongoing, B Steel in Administration

AP	TL to chase up with Nick Middleton

20190502b	RL	Update to Credit Rating following year end account - Completed

20190505a	TL	Circulate new drawings from Woods - Completed

20190505b	KW	Circulate Approved Press Release - Completed

20190507	RL	Email list to RH to confirm – AP to now show TL as owner

20190508a        RL/ PR	Attend RDPE Workshop event - Completed

20190508b	RL	Confirm Public Liability Insurance to WTC – ongoing

AP	KW to check Pier email account, and advise RL if acknowledgement received

20190509a	KW	Record Humberside Interview of 17/4/2019 – TL Completed

20190509b	TL	Check all press releases on Web Page - Completed

20190511	KW	Source ERYC Community Asset policy – Completed

AP	PR to look into nominating Pier Towers as a Community Asset

3	Minutes of Last Meeting					Accepted

4	Matters Arising from Minutes Of Last Meeting		None raised

5	Chairman’s’ Report

1) RDPE

The application form has now been submitted, along with supporting documentation, and confirmation of receipt has been received, so we are now awaiting the decision. The Spreadsheet associated with the application was populated and submitted, for Costs, Construction, plus three years after. Although estimated (QS) costs were used, these were followed up by actuals. RDPE will not consider “contingencies”, just actual costs.

2) Funding- Current Status.

£   10000 WPPA Funds

£    6000 Harold Bowler,

£    3500 WTC promissory (Note – DE took no part in WTC deliberations on this matter),

£   38500 ECCF

£175000 approx. from RDPE (Fluctuation in Euro value),

£233000 in total. Projected construction costs come out at around £250000

2) Loan

We may need to apply for a loan for any shortfall on costs. It appears that Big Local may be able to do a loan, through the Local Trust, in turn through Key Fund. Applications can be submitted, and the promise of a loan made – note that application needs to be submitted by mid-June, for August clearance.

AP	RL to forward email to TL for the Key Fund

3) Quotations

The Chairman explained the tenders which had gone out, and circulated a copy of these, showing the responses received to date. RDPE requires three quotations, or if less, twelve declines. TL had also contacted a number of companies direct for prices to check costings. Discussions took place around areas where the WPPA could reduce some of the costs, and also about at what point the WPPA would consider that costs are above an acceptable level before we go ahead.

4) Drawings

Revised drawings had been received, showing the inner (support) legs for the platform to be straight.

6	Secretary’s Report

A number of the larger companies in Hull had been contacted by email and by webpage forms. No response has been received to date

Follow up letter of progress sent to HRH Prince of Wales, as a courtesy

7	Treasurer’s Report

The Treasurer presented and circulated the WPPA accounts up to 31/5/2019

To date, the WPPA has raised £40225.13 	Members now stands at 170            Sponsors     to date 138.

8	Fundraising Report

It was noted that RH has been very proactive in raising the number of memberships, and is to be commended for his efforts in this.

AP	GH to contact new owners of KCom in Hull

Easyfundraising – The total from this web-based source now stands at £78 raised so far

RH to meet with Patrington Haven, regarding a fundraising event

Talks to go ahead with the Withernsea RBL around the use of Pier Towers as a museum for them, this may attract funding from a number of sources.

Suggested that Withernsea Sands be approached.

9	News and Media Report

The Holderness Gazette dated May 23rd carried an excellent article by Nicola Watson

Similar article appeared in the Holderness Heartbeat magazine

AP	GH mentioned a radio interview with Humberside, approximately one month ago GH to source

The WPPA Web page has been fully updated

10	Links With Other Groups

Yorkshire Bid – A letter of Support has been received from this body, which provides support for our Application to the RDPE

The Hunstanton Pier Group continue to progress, KW is in contact with John Bridger

AP	National Piers Society AGM weekend Clacton. KW to attend and report back

11 	A.O.B.

AP	TL/PR to assess the Key Fund, using experience from other submissions

Pier towers handover – No communications received, this is still ongoing

12	Next Meeting

19:00 4/7/2019 – High Brighton Street, Withernsea

Meeting closed at 21:39

Action Point Review

Colour code        DE       GH       TL       KW       RH       RL        PR

Agenda Item	Owner	Descriptor

20180311a	TL	Plaque display

20180808i	DE	Chase up Sand Le Mere sponsorship/donation

20181005b	RL	Enquire regarding insurance

20181208a	DE	Source main funding

20190502a	TL	Contacts at Siemens/British Steel

20190507	TL	Email list to RH to confirm sponsors and members

20190508b	RL	Confirm Public Liability Insurance to WTC

20190602a	TL	Written confirmation boards can be mounted on Pier Towers

20190602b	TL	Chase up Nick Middleton (Smiles)

20190602c	KW	Check WPPA emails for Insurance email for RL

20190602d	PR	Look into nomination of Community Asset

20190605	RL	Forward Key fund email to TL

20190608	GH	Contact KCom owners

20190609	GH	Source Radio interview

20190610	KW	Attend NPS AGM and report back

20190611          TL/PR 	Assess Key Fund loan application